## CostEstimate_Template
Activity | Resource | Effort Estimate per Role (hours) | Hourly Rate | Cost per Role | Cost per Activity | Cost per Phase | % of Total Cost per Phase | 200000 | Budget
1. Project Management
Developing a project charter | Project Manager | 24 | 100 | 2400 | 2400
Developing a project management plan | Project Manager | 16 | 100 | 1600 | 1600
Scheduling analysis and design meetings | Project Manager | 16 | 100 | 1600
| Business Analyst | 16 | 60 | 960
Activity SubTotal |  |  |  |  | 2560
Identifying stakeholders and defining their roles/responsibilities | Project Manager | 8 | 100 | 800
| Human Resources | 12 | 60 | 720
Activity SubTotal |  |  |  |  | 1520
Establishing governance structures | Project Manager | 12 | 100 | 1200 | 1200
Setting up communication channels and protocols | Project Manager | 12 | 100 | 1200
| Human Resources | 12 | 60 | 720
Activity SubTotal |  |  |  |  | 1920
Secure budget and approvals | Project Manager | 4 | 100 | 400
| Finance | 4 | 60 | 240
Phase Total Hours |  | 136
Activity SubTotal |  |  |  |  | 640
Phase Subtotal | [5 empty] | 11840 | 5.92%
2. Requirementts Defination
Conducting as-is analysis | Business Analyst | 60 | 60 | 3600 | 3600
Define requirements (business, stakeholder, functional, non-functional, transition) | Business Analyst | 24 | 60 | 1440
| Project Manager | 8 | 100 | 800
Activity SubTotal |  |  |  |  | 2240
Risk analysis & mitigation planning | Project Manager | 16 | 100 | 1600
| Business Analyst | 16 | 60 | 960
Activity SubTotal |  |  |  |  | 2560
Establishing a change management process | Project Manager | 16 | 100 | 1600 | 1600
Phase Total Hours |  | 140
Phase Subtotal | [5 empty] | 10000 | 5%
3. Website Design
3.1 Registration for recreational programs
Create System Architecture & Wireframes | Business Analyst | 40 | 60 | 2400
| Programmer-1 | 80 | 60 | 4800
| Programmer-2 | 80 | 60 | 4800
Activity SubTotal |  |  |  |  | 12000
Develop Program Catalog Module Design | Programmer-1 | 40 | 60 | 2400
| Programmer-2 | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 4800
3.2 Registration for classes and programs
Develop Incentive Engine Design (policy, data/ledger, algorithms) | Business Analyst | 40 | 60 | 2400
| Programmer-2 | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 4800
3.3 Tracking system
Design PET AI Assistant Features (algorithms, APIs/events) | Programmer-1 | 144 | 60 | 8640
| Programmer-2 | 144 | 60 | 8640
| Business Analyst | 80 | 60 | 4800
Activity SubTotal |  |  |  |  | 22080
3.4 Performance Motivation Engine
Integration Planning | Business Analyst | 16 | 60 | 960
| Programmer-1 | 56 | 60 | 3360
| Programmer-2 | 56 | 60 | 3360
Phase Total Hours |  | 856
Activity SubTotal |  |  |  |  | 7680
Phase Subtotal | [5 empty] | 51360 | 25.68%
4. Website Build and Developemnt
4.1 Registration for recreational programs
Configure Program Catalog | Programmer-1 | 80 | 60 | 4800 | 4800
4.2 Registration for classes and programs
Build Registration & Attendance Module (class variation) | Programmer-1 | 120 | 60 | 7200
| Programmer-2 | 120 | 60 | 7200
Activity SubTotal |  |  |  |  | 14400
4.3 Tracking system
Build Health Management Modules (APIs, engine, integration) | Programmer-1 | 120 | 60 | 7200
| Programmer-2 | 120 | 60 | 7200
Activity SubTotal |  |  |  |  | 14400
Develop PET AI Coaching System | Human Resources | 40 | 60 | 2400
| Programmer-1 | 96 | 60 | 5760
| Programmer-2 | 96 | 60 | 5760
Activity SubTotal |  |  |  |  | 13920
Develop Analytics & Reporting Layer | Programmer-2 | 88 | 60 | 5280 | 5280
4.4 Performance Motivation Engine
Develop Incentive Engine | Human Resources | 32 | 60 | 1920
| Finance | 32 | 60 | 1920
| Programmer-1 | 96 | 60 | 5760
| Programmer-2 | 96 | 60 | 5760
Activity SubTotal |  |  |  |  | 15360
First Demo | Project Manager | 8 | 100 | 800
| Programmer-1 | 8 | 60 | 480
Activity SubTotal |  |  |  |  | 1280
Integration | Programmer-1 | 120 | 60 | 7200 | 7200
Phase Total Hours |  | 1272
Phase Subtotal | [5 empty] | 76640 | 38.32%
5. Testing
Develop test plans and scripts | Business Analyst | 8 | 60 | 480
| End Users - 1 | 8 | 60 | 480
| End Users - 2 | 8 | 60 | 480
| Programmer-1 | 24 | 60 | 1440
Activity SubTotal |  |  |  |  | 2880
| Programmer-1 | 40 | 60 | 2400
Conduct system testing | End Users - 3 | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 4800
| Programmer-1 | 40 | 60 | 2400
Conduct integration testing | End User - 4 | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 4800
User acceptance testing | End Users-1 | 40 | 60 | 2400
| End Users-2 | 40 | 60 | 2400
| End Users-3 | 40 | 60 | 2400
| End Users-4 | 40 | 60 | 2400
| End Users-5 | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 12000
Defect resolution & re-testing | Programmer-1 | 40 | 60 | 2400
| End Users-3 | 24 | 60 | 1440
| End Users-4 | 24 | 60 | 1440
Activity SubTotal |  |  |  |  | 5280
| Project Manager | 4 | 100 | 400
Training materials (transition docs, workshop prep) | Business Analyst | 16 | 60 | 960
| Human Resources | 16 | 60 | 960
Activity SubTotal |  |  |  |  | 2320
Finalize testing phase | Project Manager | 4 | 100 | 400
| Business Analyst | 4 | 60 | 240
Activity SubTotal |  |  |  |  | 640
Phase Total Hours |  | 540
Phase Subtotal | [5 empty] | 32720 | 16.36%
6. Training, rollout, and support
Data conversion | Programmer-2 | 24 | 60 | 1440
| Hardware Specialist | 24 | 60 | 1440
Activity SubTotal |  |  |  |  | 2880
Deploy to production | Programmer-1 | 24 | 60 | 1440
| Hardware Specialist | 24 | 60 | 1440
Activity SubTotal |  |  |  |  | 2880
| Project Manager | 8 | 100 | 800
End-user training | Business Analyst | 8 | 60 | 480
| Human Resources | 32 | 60 | 1920
| End User - 1 | 8 | 60 | 480
Activity SubTotal |  |  |  |  | 3680
| Project Manager | 8 | 100 | 800
Execute deployment | Programmer-2 | 8 | 60 | 480
| Hardware Specialist | 20 | 60 | 1200
Activity SubTotal |  |  |  |  | 2480
Monitor stability | Hardware Specialist | 30 | 60 | 1800
| Programmer-1 | 30 | 60 | 1800
Activity SubTotal |  |  |  |  | 3600
| Project Manager | 4 | 100 | 400
| Programmer-1 | 4 | 60 | 240
| Programmer-2 | 4 | 60 | 240
Go/No-Go meeting | Hardware Specialist | 4 | 100 | 400
| Business Analyst | 4 | 60 | 240
Activity SubTotal |  |  |  |  | 1520
Go Live | Project Manager | 4 | 100 | 400
| Programmer-1 | 4 | 60 | 240
| Programmer-2 | 4 | 60 | 240
| Hardware Specialist | 4 | 60 | 240
| Business Analyst | 4 | 60 | 240
Activity SubTotal |  |  |  |  | 1360
Hypercare | Hardware Specialist | 160 | 60 | 9600
| Programmer-1 | 160 | 60 | 9600
Activity SubTotal |  |  |  |  | 19200
Transition to support team | Project Manager | 16 | 100 | 1600
| Human Resources | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 4000
Lessons learned workshop | Project Manager | 8 | 100 | 800
| Business Analyst | 8 | 60 | 480
| Human Resources | 40 | 60 | 2400
Activity SubTotal |  |  |  |  | 3680
Close vendor contracts | Project Manager | 8 | 100 | 800
| Finance | 8 | 60 | 480
Activity SubTotal |  |  |  |  | 1280
Document final deliverables | Project Manager | 8 | 100 | 800
| Business Analyst | 8 | 60 | 480
Activity SubTotal |  |  |  |  | 1280
Release project resources | Project Manager | 8 | 100 | 800
| Business Analyst | 8 | 60 | 480
Activity SubTotal |  |  |  |  | 1280
Final closure | Project Manager | 4 | 100 | 400 | 400
Phase Total Hours |  | 772
Phase Subtotal | [5 empty] | 49520 | 24.76%
Project Contingencies | [5 empty] | 20000 | 10%
Total Cost Estimate | [5 empty] | 252080