## Sheet1
Name | Position | Internal/External | Project Role | Contact Information
David Chan | Project Manager | Internal | Project Lead | dchan@hwi.com
Nina Patel | VP of Human Resources | Internal | Project Co-Sponsor | npatel@hwi.com
Mark Rivera | VP of Finance | Internal | Project Co-Sponsor | mrivera@hwi.com
Omar | HR Specialist | Internal | Subject Matter Expert (HR) | omar@hwi.com
Isla Romano | Finance Specialist | Internal | Subject Matter Expert (Fin) | iromano@hwi.com
Liam Kapoor | Programmer / AI Specialist | Internal | Lead Developer / AI Tech Lead | lkapoor@hwi.com
Ethan Morales | Programmer | Internal | Developer | emorales@hwi.com
Patrick Lamar | Hardware Specialist | Internal | Infrastructure Support | plamar@hwi.com
Chloe Nguyen | Business Analyst | Internal | Requirements Lead | cnguyen@hwi.com
Noah Zhang | Hardware Specialist | Internal | Support Role | nzhang@hwi.com
BrightPath Consultants | Training & Incentive Partner | External | Vendor / Implementation Partner | contact@brightpathconsult.com
End Users | Employees | Internal | System Users | All internal staff (7,500)

## Sheet2
Name | Power / Interest (High/Medium/Low) | Current Engagement Level | Potential Management Strategies
David Chan | High / High | Actively Engaged | Maintain daily stand-ups; use clear reporting; ensure continuous risk and scope management.
Nina Patel | High / High | Highly Engaged | Provide regular high-level updates; involve in milestone reviews; align with HR strategic goals.
Mark Rivera | High / High | Highly Engaged | Present clear financials; involve in budget reviews; emphasize ROI; formal communication preferred.
Liam Kapoor | High / High | Overly Involved | Channel technical enthusiasm; set clear priorities; limit scope influence; regular technical check-ins.
Chloe Nguyen | Medium / High | Actively Engaged | Support requirements process; ensure clear documentation; facilitate stakeholder workshops.
Omar | Medium / High | Highly Engaged | Formalize feedback process; involve in UAT; prevent scope creep via PM coordination.
Isla Romano | Medium / Medium | Moderately Engaged | Provide structured financial data; align with Omar carefully; formal updates.
Ethan Morales | Medium / Medium | Engaged | Assign clear tasks; peer reviews; align with Liam on technical delivery.
Patrick Lamar | Medium / Medium | Engaged | Monitor availability; plan for knowledge transfer; engage during integration phases.
Noah Zhang | Low / Medium | Limited Engagement | Engage as needed; assign specific infrastructure tasks; monitor performance.
BrightPath Consultants | Medium / Medium | Contractually Engaged | Manage via SOW; regular progress reviews; align training with rollout schedule.
End Users | Low / High | Not Yet Engaged | Conduct surveys & focus groups; involve pilot groups; provide clear training & communication.

## Sheet3
Metric | Formula | Calculation | Result
Cost Variance (CV) | EV – AC | 58,560 – 58,560 | 0
Schedule Variance (SV) | EV – PV | 58,560 – 58,560 | 0
Cost Performance Index (CPI) | EV ÷ AC | 58,560 ÷ 58,560 | 1
Schedule Performance Index (SPI) | EV ÷ PV | 58,560 ÷ 58,560 | 1
Estimate at Completion (EAC) | BAC ÷ CPI | BAC ÷ 1.0 | BAC

## Sheet4
Workstream | Duration Change | How We’ll Achieve It
Create System Architecture & Wireframes | 18 → 15 (-3d) | Run the RAG content model in parallel with Information Architecture & Sitemap work to remove idle time.
Develop Incentive Engine Design | 25 → 20 (-5d) | We will put one extra engineer on this
Integrations Development | 15 → 10 (-5d) | We will put one extra engineer on this
Testing | 23 → 20 (-3d) | Run Training Materials (transition docs, workshops) in parallel with defect resolution & retesting; eliminate wait time between test cycles and enablement.
Deployment / End-User Training | Overlap saves -4d | Conduct End-User Training in parallel with Production Deployment with a one-day lag to align with deployment activities; removes inactive calendar days.