# Strategy: Bringing the HealthyWorks Digital Wellness Portal Project Back on Track and On Budget

## 1. Current Performance Overview

At the three-month checkpoint, the project reported the following metrics:
• Planned Value (PV) = $100,000
• Earned Value (EV) = $90,000
• Actual Cost (AC) = $115,000

These figures yield a Cost Performance Index (CPI) of 0.78 and a Schedule Performance Index (SPI) of 0.90, indicating the project is both over budget and behind schedule. The recovery strategy aims to improve CPI > 0.95 and SPI ≥ 1.0 by the next phase gate review.

## 2. Recovery Objectives

• Recover three to four weeks of schedule delay through optimized sequencing and parallel execution.

• Reduce cost variance from +15.5% to ≤ +5% by optimizing resource utilization and trimming low-value activities.

• Restore confidence in project governance and reporting accuracy.

• Preserve core functionality for go-live while deferring non-critical enhancements to Phase 2.

## 3. Key Corrective Actions

### A. Scope Optimization

To reduce unnecessary workload and expenditure, the following de-scoping measures will be implemented:
• Retain essential modules: Program Registration, Incentive Management, and Tracking System.
• Defer advanced PET AI coaching enhancements and gamified leaderboards to Phase 2.
• Simplify analytics dashboards to baseline KPI reporting.
• Expected savings: 10–15% of build cost (≈ $20–$30K).

### B. Schedule Compression

To regain schedule momentum, two schedule compression strategies will be applied:
• Fast-Tracking – Overlap key activities such as testing, training preparation, and user documentation.
• Crashing – Assign additional resources to critical-path modules (Tracking System, Incentive Engine) to shorten duration.
• Combined impact: recover up to four weeks of project delay while maintaining quality.

### C. Resource Optimization

Resource utilization will be balanced to improve productivity and reduce overtime:
• Reassign analysts and testers to support concurrent tasks (QA, documentation, UAT prep).
• Deploy temporary development support for AI integration and testing.
• Shift training content development to HR and internal SMEs to reduce consultant cost.

### D. Cost Control and Monitoring

• Apply partial contingency release (5%) to offset AI-related overages.
• Introduce a rolling-wave cost forecast updated biweekly.
• Implement variance thresholds requiring sponsor review if CPI < 0.9 or SPI < 0.95.
• Transition to a visual dashboard tracking actual vs. forecasted cost and schedule trends.

## 4. Governance and Communication Improvements

Strong governance and stakeholder alignment are critical for maintaining schedule discipline and cost control. The following practices will be implemented immediately:
• Weekly steering committee reviews focused on scope stability and EV metrics.
• Daily stand-ups for the development and testing teams to track blockers.
• Transparent change-control log to capture and approve all scope or budget adjustments.
• Mid-phase progress reports distributed to all stakeholders with updated CPI/SPI indicators.

## 5. Expected Outcome

By implementing these corrective measures, the project is expected to achieve the following results:
• Revised Estimate at Completion (EAC): $192,000 (within $8K of target budget).
• Revised duration: 6 months total with a recovered schedule buffer of two weeks.
• Improvement of CPI from 0.78 → 0.96 and SPI from 0.90 → 1.02.
• Core features delivered on time for the scheduled go-live in January 2026.

## 6. Conclusion

The combined approach of scope rationalization, schedule compression, resource optimization, and enhanced governance provides a structured and achievable path to bring the HealthyWorks project back on track and on budget. Ongoing earned-value monitoring and transparent communication will ensure sustained performance improvement through project closeout.