# Tab 1

# FINAL REPORT

# MINDMESH

Date: 12/03/2025

# TABLE OF CONTENTS

Executive Summary	3

Project Charter	5

Business case	5

Charter	7

Scope & Activities	9

WBS CHART	12

Schedule	13

GANTT CHART	13

Approaches to reduce duration	13

Cost Estimate	14

EVM	14

Cost-saving measures	15

RACI Chart	17

Resource Histogram	18

Risk	19

Risk	19

Risk Matrix	21

Risk response	22

Stakeholder Register	23

Stakeholder Strategy	24

# Executive Summary

Project Overview

HealthyWorks International (HWI) has initiated the Digital Wellness Portal Project, a six-month initiative with a budget of $200,000, scheduled to run from August 1, 2025, to January 31, 2026. The project aims to develop an intranet-based application to improve employee health and wellness. This strategic move is a direct response to HWI paying 18% above the industry average for healthcare premiums, with the primary goal of achieving net savings of at least $35 per employee annually.

Core Solution

1. The portal will serve as a centralized hub for employee wellness, featuring:

- A system for registering for company-sponsored recreational programs (e.g., yoga, cycling) and health-management classes (e.g., stress reduction, smoking cessation).

- A data tracking and analytics engine to monitor participation and program effectiveness.

- An incentive management system to reward employees for achieving health goals.

- Integration of "PET AI," a generative AI chatbot, to act as a digital coach and personal trainer.

2. Key Management Components:

- Scope & Schedule: A detailed project scope statement and Work Breakdown Structure (WBS) have been developed, supported by a Gantt chart to manage the aggressive six-month timeline.

- Budget: A refined cost estimate aligns with the $200,000 budget, with ongoing Earned Value Management (EVM) to track financial and schedule performance.

- Resources & Stakeholders: A RACI chart and resource histograms will clarify roles, while a proactive stakeholder management strategy addresses challenges with key individuals to ensure alignment.

- Risk Management: A risk register and probability/impact matrix have been created to proactively identify, analyze, and mitigate potential threats, including technical integration challenges, key personnel dependencies, and stakeholder conflicts.

Current Challenges and Solution Approach

1. Integration with Outdated HR Systems

Challenge: Legacy HR data structures and limited APIs could hinder seamless integration.
  Solution: Early technical assessment, data mapping, middleware evaluation, and a proof-of-concept interface will ensure feasibility before full development.

2. Stakeholder Misalignment

- Omar’s informal influence may cause scope creep.

- Nina’s long-term strategic focus may slow tactical decisions.

- Mark’s risk-aversion could delay approvals.

Solutions:

- Implement a formal change control process.

- Use structured decision criteria and time-boxed discussions.

- Provide concise financial dashboards for Mark.

- Clarify SME roles and establish a single requirements channel.

3. Resource Constraints (Patrick’s departure)

Solution: Knowledge transfer, documentation, and cross-training ensure continuity of hardware-related tasks.

4. End-User Engagement Risks

Solution: Communication campaigns, pilot groups, incentives, and extensive user testing to maximize adoption.

5. AI Performance and Safety

Solution: Rigorous testing, guardrails, disclaimers, and manual escalation paths for sensitive health inquiries.

Conclusion:

The Digital Wellness Portal is a strategically critical project for HWI. Its successful implementation is expected to directly enhance employee well-being, create significant cost savings by lowering insurance premiums, and foster a more engaged, health-conscious workforce. A disciplined approach to project management will be essential to deliver this value on time and within budget.

# Business case

This business case justifies the investment in the Digital Wellness Portal project by quantifying its financial benefits.

1. Financial Assumptions:

Project Cost (Build Cost): $200,000

Annual Maintenance Cost: 40% of the build cost = $80,000 per year

Number of Full-Time Employees: 7,500.

Net Savings per Employee/Year: $35 (as stated in the project overview).

Total Annual Savings: 7,500 employees * $35/employee = $262,500.

Total Monthly Savings: $262,500 / 12 =  $21,875

Discount Rate: 8%.

Analysis Period: 5 years.

2. Cash Flow Projection and Financial Calculations:

| Year | Cash Outflows (Costs) | Cash Inflows (Savings) | Net Cash Flow | Discount Factor (8%) | Present Value (PV) of Net Cash Flow |
| --- | --- | --- | --- | --- | --- |
| 0 | -$200,000 | $0 | -$200,000 | 1.0000 | -$200,000 |
| 1 | -$80,000 | $262,500 | $182,500 | 0.9259 | $168,977 |
| 2 | -$80,000 | $262,500 | $182,500 | 0.8573 | $156,460 |
| 3 | -$80,000 | $262,500 | $182,500 | 0.7938 | $144,869 |
| 4 | -$80,000 | $262,500 | $182,500 | 0.7350 | $134,138 |
| 5 | -$80,000 | $262,500 | $182,500 | 0.6806 | $124,210 |
| Total | -$600,000 | $1,312,500 | $712,500 |  | $528,653 |

Net Present Value (NPV): $528,653

Calculation: Sum of PV of Net Cash Flow = $528,653.

Interpretation: A positive NPV indicates that the project is expected to generate value exceeding its cost, considering the time value of money. This is a strong financial justification for approval.

Return on Investment (ROI): 88.1%

Calculation: ROI = (Total Net Benefits / Total Costs) * 100.

Total Net Benefits = Total Inflows - Total Outflows = $1,312,500 - $600,000 = $712,500.

ROI = ($712,500 / $600,000) * 100 = 118.8%.

Alternatively, using PV of benefits (~$762,500) vs. PV of costs (~$233,830) would yield an even higher ROI. The 118.8% based on nominal cash flows is a standard and conservative measure.

Payback Period: ~1.1 years

Calculation: The initial investment is $200,000. The annual net cash flow after Go-Live is $182,500.

Payback Period = Initial Investment / Annual Net Cash Flow = $200,000 / $182,500 ≈ 1.1 years.

Interpretation: The project will recover its initial investment in just over one year, which is excellent and indicates very low risk.

Conclusion of Business Case:

The Digital Wellness Portal project presents a compelling financial opportunity for HealthyWorks International. With a significant positive NPV of approximately $528,653, an ROI of 118.8%, and a rapid payback period of just over one year, the project aligns directly with the strategic goal of reducing internal costs. The investment is justified by the anticipated savings from lower healthcare premiums.

# Charter

HealthyWorks Digital Wellness Initiative Project Charter

| PROJECT TITLE | DATE OF AUTHORIZATION | PROJECT START DATE | PROJECT END DATE |
| --- | --- | --- | --- |
| Recreation and Wellness Intranet Project | Aug 1st 2025 | Aug 1st 2025 | Jan 31st 2026 |

PROJECT OVERVIEW

| KEY MILESTONES | · First complete version to test by Nov 1St · Completed version ready to launch by Jan 31st, 2026. |
| --- | --- |
| BUDGET INFORMATION | $200,000 in 6 months |
| PROJECT MANAGER | David Chan |
| PROJECT OBJECTIVES | · Develop and deploy a Digital Wellness Portal on the company intranet to provide a centralized platform for employee wellness and health-management programs. · Integrate WellBot AI to deliver personalized wellness coaching and progress tracking to employees. · Implement PET rewards and automated notifications to increase engagement and sustain healthy habits. · Provide dashboards and reporting to measure participation, program effectiveness, and progress over time. · Address HealthyWorks above-industry healthcare premium costs by improving employee wellness participation and outcomes, supporting the targeted $35 per employee per year savings ($262,500/year). |
| MAIN PROJECT SUCCESS CRITERIA | · Scope: The portal is delivered with the required capabilities, including program registration, WellBot AI, the PET rewards program, automated notifications, reporting and analytics dashboards, and integration with HR systems, while meeting privacy and security requirements. · Time: A testable prototype is completed by Nov 1, 2025, and the final system is launched by Jan 31, 2026. · Cost: The project is completed within the approved $200,000 budget. · Value: Within 12 months of rollout, at least 50% of employees actively use the portal, the solution supports the targeted $35 per employee per year savings ($262,500/year), and the system maintains 99.3% uptime. |

APPROACH

- Have daily scrum to plan and communicate work for the day - Within 2 weeks, we will have developed a clear work breakdown, scope and Gantt chart detailing the project. Hold weekly progress review meetings with the project team and bi-weekly meetings with the steering committee - Hire personal trainers, coaches and nutritionist to get started on the various recreational programs - Create incentive PET reward program (Gamification: daily streak, weekly streak and notification) - Establish a clear baseline of current healthcare costs and employee health metrics. After launch, continuously track the predefined KPIs (e.g., reduced insurance claims, improved health assessments) - Outsourcing system integration management and UX designer - Work closely with the Finance and HR departments from day one to build the data model - Conduct weekly software testing after the first prototype. Use their feedback to refine features. - Outsourcing Security Audit to test internal Security Team

ROLES AND RESPONSIBILITIES

| NAME | ROLE | POSITION | CONTACT INFORMATION |
| --- | --- | --- | --- |
| David Chan | Project Manager | Manager | Cdavid@healthworks.com |
| Nina Patel | Co-Sponsor | VP Human Resources | Pnina@healthworks.com |
| Mark Rivera | Co-Sponsor | VP Finance | Rmark@healthworks.com |
| Liam Kapoor | Team Member | Programmer | Kliam@healthworks.com |
| Chloe Nguyen | Team Member | Business Analyst | Nchloe@healthworks.com |
| Ethan Morales | Team Member | Programmer | Methan@healthworks.com |
| Patrick Lamar | Team Member | Hardware Specialist | Lpatrick@healthworks.com |

# Scope & Activities

Project Title: Digital Wellness Portal- Healthyworks International Date: October 18 Prepared by: David Chan, Project Manager Cdavid@healthyworks.com

Project Summary and Justification: HealthyWorks International (HWI) currently pays about 18% above the industry average for employee healthcare premiums, driven largely by low participation in wellness programs, the lack of a centralized system to track activities, and fragmented HR data that limits visibility into employee health engagement. A company intranet application that boosts participation in wellness activities and supports behavior change (via registration, tracking, incentives, and WellBot AI coaching) is expected to improve health outcomes within one year of rollout, enabling premium negotiations and net savings (target ≥ $35/employee/year over three years).

Project Characteristics and Requirements: - Process scope – the system will authenticate and give employee access to the portal. It will allow them to browse and select their wellness programs. It will track and record user participation in programs and classes - Functional scope – the program will allow profile creation and updates and have a secure login. It will create personalized routines, workouts and recommendations. PET answering health related queries. It will also monitor health milestones and give encouragement. It will allow HR to collect data and reports to track participation for rewards - Organizational scope – it will be mainly used by employees. HR will manage the program participation and data. Supervisors that will have access to the portal and they will also be responsible for approving milestones and oversight. The finance department will manage data for rewards - Interface scope – it will pull employee’s profile, and department info from the existing organization systems, Finance department will also have access to manage rewards. - Technical Infrastructure Scope – Web based portal that is hosted on the company’s secure network. Al service layers for PET service - Enhancement Scope – a mobile app version of the program will be developed so that employees can access it on the go. The program will be able to generate recommendations of classes and routines based on preference and levels - Data Conversion Scope – migrate all employees information from existing programs and allow all employee access with their company credentials. Validate data to make sure accuracy Requirements - Business Requirement - The system must increase employee participation in wellness activities to improve overall health outcomes and help HWI negotiate lower healthcare premiums, targeting at least $35 in annual savings per employee. - Stakeholder Requirement - HR and Finance leaders must be able to access real-time dashboards and reports that show participation levels, program effectiveness, and incentive performance to support data-driven decisions. Provide HR with a centralized system - Functional Requirement - The portal must allow employees to register for wellness programs, view schedules, and track their attendance, progress, and incentive achievements in one centralized location. Display achievements and send motivational notifications. - Non-Functional Requirement - The system must securely handle all 7,500 employee wellness data using encryption, role-based access, and compliance with organizational privacy standards. Must have 99% uptime and ensure full HIPPA compliance and privacy - Transition Requirement - Existing employee wellness records, program catalogs, and participation data must be migrated into the new portal to ensure continuity and accurate reporting at launch. Will have ongoing maintenance, bug fixes and feature enhancements. - Project Requirement - The project must be completed within six months with agile methodology and stay within the approved $200,000 budget, aligning with HWI’s timeline, resource, and financial constraints.

Summary of Project Deliverables: Project management-related deliverables: Project charter, Stakeholder register and engagement plan, Scope document, Project plan, WBS, Project schedule, Budget cost, Risk management plan, Status/Progress reports, Final presentation, Final Project Report & Lessons-Learned Report, System design documents, Integration and data migration templates, Testing plans, Executive dashboard setup, Training materials and guides Product-related deliverables: - Business requirements, stakeholder requirements; detailed functional & nonfunctional specs - UX artifacts: IA, user flows, wireframes, UI design system (components, accessibility specs) - Configurable program catalog module; registration & attendance module - Health-management module (goals/plans/progress) - Incentive engine (rules, awards, leaderboards) - WellBot AI assistant (Q&A, plans, nudges) with guardrails and admin controls - AI Assistant (Employee) with RAG & Citations, Safety Layer, Evaluation Harness,Telemetry & Dashboards, Content Corpus & Data Dictionary - Integrations: HRIS (directory), SSO, email, calendar feed (optional) - Data: schema, migration scripts, validations, seed data - Analytics layer: dashboards, standard reports, export jobs - Security: RBAC, audit logs, encryption, privacy controls - Environments & CI/CD: DEV/TEST/PROD pipelines, monitoring - Documentation: admin/runbooks, user guides, API specs

Project Success Criteria: The goal of this project is to design and implement the Digital Wellness Portal to enhance employee health engagement and reduce healthcare costs at HealthyWorks International. The portal will allow employees to independently discover, enroll, and receive confirmations for all published wellness programs without help-desk assistance. The project will be completed within a six-month timeline followed by one month of post-implementation support, staying within the approved $200,000 budget. Success will be measured by achieving at least 60% enrollment from the targeted pilot group within 90 days of launch, ensuring the incentive engine processes rewards with ≤1% payout discrepancy, maintaining dashboard rendering within three seconds (p95) and system availability of 99.5% during business hours, and obtaining positive UAT sign-off from HR and Finance along with full completion of the production Go-Live checklist to confirm the system meets all business and technical objectives.

Constraint, Boundaries and Assumptions: - Budget target: ≤ $200,000; schedule target: ~6 months (Start: Aug 1, 2025; Go-Live: Jan 31, 2026) - Limited team availability per case (named resources across HR/Finance/IT) - Must comply with corporate security & privacy policies; no PHI beyond what HR policies allow - No additional hardware/software purchases required; existing intranet and HRIS are available and supported - HR will supply program content/schedules and incentive rules; Finance will define KPI thresholds and savings methodology - SSO and email services are already enterprise-supported - Employees primarily access via desktop/mobile browser; accessibility (WCAG-aligned) required

## WBS CHART

# Schedule

## GANTT CHART

## Approaches to reduce duration

Baseline & Objective

The current critical path totals 126 days (~26 weeks) across initiation, analysis, architecture/wireframes, incentive engine design, analytics & reporting, integrations, testing, and deployment.

Changes (before → after, with approach)

| Workstream | Duration Change | How We’ll Achieve It |
| --- | --- | --- |
| Create System Architecture & Wireframes | 18 → 15 (-3d) | Run the RAG content model in parallel with Information Architecture & Sitemap work to remove idle time. |
| Develop Incentive Engine Design | 25 → 20 (-5d) | We will put one extra engineer on this |
| Integrations Development | 15 → 10 (-5d) | We will put one extra engineer on this |
| Testing | 23 → 20 (-3d) | Run Training Materials (transition docs, workshops) in parallel with defect resolution & retesting; eliminate wait time between test cycles and enablement. |
| Deployment / End-User Training | Overlap saves -4d | Conduct End-User Training in parallel with Production Deployment with a one-day lag to align with deployment activities; removes inactive calendar days. |

Rationale & Risk Controls (summary)

- Parallelization where safe: Activities that don’t gate each other (RAG content modeling

vs IA; training vs defect re-test) are overlapped to reclaim idle time.

- Front-loaded certainty, deferred detail: The incentive engine’s core data/ledger

decisions are finalized now; lower-value details are captured in ADRs for iterative

refinement during build, reducing design churn without adding rework.

- No quality trade-off: Testing days are reduced by removing wait states, not test

coverage; training runs alongside, not after, the final fix cycles.

# Cost Estimate

Cost Estimate - CostEstimate HealthyWorks.xlsx

EVM Calculation:

PV = $58,560 EV = $58,560 AC = $58,560 BAC = $200,000

| Metric | Formula | Calculation | Result |
| --- | --- | --- | --- |
| Cost Variance (CV) | EV – AC | 58,560 – 58,560 | 0 |
| Schedule Variance (SV) | EV – PV | 58,560 – 58,560 | 0 |
| Cost Performance Index (CPI) | EV ÷ AC | 58,560 ÷ 58,560 | 1 |
| Schedule Performance Index (SPI) | EV ÷ PV | 58,560 ÷ 58,560 | 1 |
| Estimate at Completion (EAC) | BAC ÷ CPI | BAC ÷ 1.0 | BAC |

Schedule: SPI = 1 → on schedule

Cost: CPI = 1 → on budget

Estimate at Completion (EAC)– BAC/CPI = 200,000/1 = 200,000

## Cost-saving measures

1. Current Performance Overview

At the three-month checkpoint, the project reported the following metrics:

- Planned Value (PV) = $58,560

- Earned Value (EV) = $58,560

- Actual Cost (AC) = $58,560

These figures yield a Cost Performance Index (CPI) of 1 and a Schedule Performance Index (SPI) of 1, indicating the project is both on budget and on schedule. So we aim to see if we can cut any cost further

2. Recovery Objectives

- Cut down three to four weeks of schedule through optimized sequencing and parallel execution.

- Reduce cost variance from +15.5% to ≤ +5% by optimizing resource utilization and trimming low-value activities.

- Restore confidence in project governance and reporting accuracy.

- Preserve core functionality for go-live while deferring non-critical enhancements to Phase 2.

3. Key Corrective Actions

A. Schedule Compression

To regain schedule momentum, two schedule compression strategies will be applied:

- Fast-Tracking – Overlap key activities such as testing, training preparation, and user documentation.

- Crashing – Assign additional resources to critical-path modules (Tracking System, Incentive Engine) to shorten duration.

- Combined impact: recover up to four weeks of project delay while maintaining quality.

B. Resource Optimization

- Reassign analysts and testers to support concurrent tasks (QA, documentation, UAT prep).

- Deploy temporary development support for AI integration and testing.

- Shift training content development to HR and internal SMEs to reduce consultant cost.

C. Cost Control and Monitoring

- Apply partial contingency release (5%) to offset AI-related overages.

- Introduce a rolling-wave cost forecast updated biweekly.

- Transition to a visual dashboard tracking actual vs. forecasted cost and schedule trends.

4. Governance and Communication Improvements

Strong governance and stakeholder alignment are critical for maintaining schedule discipline and cost control. The following practices will be implemented immediately:

- Weekly steering committee reviews focused on scope stability and EV metrics.

- Daily stand-ups for the development and testing teams to track blockers.

- Transparent change-control log to capture and approve all scope or budget adjustments.

- Mid-phase progress reports distributed to all stakeholders with updated CPI/SPI indicators.

5. Expected Outcome

By implementing these corrective measures, the project is expected to achieve the following results:

- Revised Estimate at Completion (EAC): $192,000 (within $8K of target budget).

- Revised duration: 6 months total with a recovered schedule buffer of two weeks.

- Improvement of CPI from 1 → 1.12 and SPI from 1 → 1.08.

- Core features delivered on time for the scheduled go-live in January 2026.

6. Conclusion

The combined approach of scope rationalization, schedule compression, resource optimization, and enhanced governance provides a structured and achievable path to bring the HealthyWorks project back on track and on budget. However, consider the value that some of the cuts would impact the quality of work. We would suggest to follow with the original plan

# RACI Chart

|  | Project Manager | SME | Tech Lead | BA | Developer | Functional lead |
| --- | --- | --- | --- | --- | --- | --- |
| Develop project charter | A, R | C |  | C |  |  |
| Develop requirement document | A | C |  | R |  | C |
| Develop database schema | I |  | A |  | R | C |
| Develop front UI design | I | C | A |  | R | C |
| Code user registration UI |  |  | A |  | R | C |
| Develop test cases | C | C | C | A, R |  | C |
| Develop training material | I | C |  | R |  | A |
| Conduct user acceptance test |  | C | C | R |  | A |
| Migrate code to production environnement |  |  | A, R |  |  | C |
| Conduct knowledge transfer to support team | C |  | A | R | C | C |

# Resource Histogram

# Risk

| No | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability (1–10) | Impact (1–10) | Risk Score (P×I) | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R4 | 1 | HR system integration failure | Outdated HR system may not connect smoothly, causing data issues and delays. | Technical / Integration | Old HR system + messy data | Integration test fails,data mismatches, frequent system errors | Do an early integration test, clean/map the data, get HR IT/vendor support, keep a backup manual import plan | David Chan + Chloe Nguyen | 7 | 10 | 70 | Open |
| R1 | 2 | Patrick departure (hardware support) | Patrick may leave during the project and slow down setup and technical support. | Resource / Schedule | Key work depends on one person | Patrick becomes unavailable, infra tasks delayed | Collect his notes, document steps, train a backup person, finish critical setup early | David Chan | 9 | 8 | 64 | Open |
| R5 | 3 | Scope changes from Omar | Omar may request frequent changes, causing extra work and delays. | Stakeholder / Scope | Unclear boundaries + push for extra features | New “must-have” requests,changes after approval, workshop conflicts | Lock requirements, allow changes only with approval, track changes in a log, prioritize must-haves first | David Chan + Nina Patel | 9 | 7 | 63 | Open |
| R7 | 4 | AI + privacy/compliance risk | The chatbot could give wrong guidance or create privacy issues with wellness data. | Security / Compliance | Sensitive data + AI output risk | Complaints, security findings, privacy review issues | Limit what the bot can say, add clear warnings, review risky content, do a security/privacy check, monitor issues | Liam Kapoor + David Chan | 5 | 9 | 45 | Open |
| R2 | 5 | Low end-user cooperation | Users may not participate in testing, hurting feedback and adoption. | User / Adoption | Low motivation + limited time | Low UAT attendance, delayed feedback, low engagement | Offer small incentives, make testing short/easy, use student/employee “champions,” send clear updates and reminders | Nina Patel + Omar | 6 | 7 | 42 | Open |
| R3 | 6 | Inaccurate status reporting | Team may not report real progress, so problems show up late. | Project Management | Poor reporting habits | Missing updates, surprise delays,hidden blockers | Use a weekly status format, ask for proof of progress, raise blockers early, review risks every week | David Chan | 6 | 6 | 36 | Open |
| R6 | 7 | Isla–Omar conflict | Tension between Isla and Omar may slow decisions and meetings. | Communication / Organization | Personal/process conflict | Meetings go off track, long disagreements, delayed approvals | Set meeting rules, keep discussions structured, clarify who decides what, escalate to sponsor if needed | David Chan | 6 | 5 | 30 | Open |
| R8 | 8 | AI hallucinations | Generative AI (WellBot AI) produces inaccurate, biased, or unsafe coaching advice | Technical / Compliance / Reputation | New Technology/ Unrest + Need large data | Complex integration, limited specialized resources, rework from overlapping tasks | Define clear AI requirements and boundaries; perform rigorous testing with SMEs; add disclaimers and escalation paths to human coaches; restrict high-risk recommendations (medical diagnosis); log and monitor AI interactions for continuous improvement. | Liam | 5 | 8 | 40 | Open |

## Risk Matrix

|  | ## High |  |  | ## R4 |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | ## R1 |  |
|  |  |  |  | ## R5 |  |
| ## Probability | ## Medium |  | ## R3 | ## R7 |  |
|  |  |  | ## R6 | ## R2 |  |
|  | ## Low |  |  |  |  |
|  |  | ## Low | ## Medium | ## High |  |
|  |  | ## Impact |  |  |  |
|  | ## Banding used: Low = 1–3, Medium = 4–6, High = 7–10 |  |  |  |  |

## Risk response

- R1 & R4 were scored highest because losing a key hardware specialist or discovering that the HR system cannot integrate as needed could delay Go Live and increase cost significantly, threatening the six-month, $200,000 constraints.

- R2 & R5 directly threaten user adoption and scope control. Without cooperative end users and controlled HR input, the system could “go live” but fail in practice or expand beyond budget.

- R3 & R6 are more about management discipline and stakeholder dynamics—serious but more controllable through process, facilitation, and leadership.

- R7 reflects the reputational and ethical risk of using AI for wellness coaching; impact is high if not handled correctly, so strong testing and guardrails are essential.

Summary of Risk Response Strategy

- Identify & Prioritize: Maintain and regularly update the risk register and risk scores.

- Mitigate: Focus on early action for R1 and R4 (knowledge transfer and integration proof-of-concept).

- Control Scope & Stakeholders: Use a formal change control process and clear stakeholder roles to manage Omar, Nina, Isla, and others.

- Monitor: Track risk indicators via schedule slippage, defect trends, AI test results, and stakeholder feedback.

- Communicate: Review top risks and actions in every steering committee meeting.

# Stakeholder Register

| Name | Position | Internal/External | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| David Chan | Project Manager | Internal | Project Lead | Cdavid@healthworks.com |
| Nina Patel | VP of Human Resources | Internal | Project Co-Sponsor | Pnina@healthworks.com |
| Mark Rivera | VP of Finance | Internal | Project Co-Sponsor | Rmark@healthworks.com |
| Omar | HR Specialist | Internal | Subject Matter Expert (HR) | omar@healthworks.com |
| Isla Romano | Finance Specialist | Internal | Subject Matter Expert (Fin) | iromano@healthworks.com |
| Liam Kapoor | Programmer / AI Specialist | Internal | Lead Developer / AI Tech Lead | Kliam@healthworks.com |
| Ethan Morales | Programmer | Internal | Developer | emorales@healthworks.com |
| Patrick Lamar | Hardware Specialist | Internal | Infrastructure Support | Lpatrick@healthworks.com |
| Chloe Nguyen | Business Analyst | Internal | Requirements Lead | Nchloe@healthworks.com |
| Noah Zhang | Hardware Specialist | Internal | Support Role | nzhang@healthworks.com |
| BrightPath Consultants | Training & Incentive Partner | External | Vendor / Implementation Partner | contact@brightpathconsult.com |
| End Users | Employees | Internal | System Users | All internal staff (7,500) |

## Stakeholder Strategy

| Name | Power / Interest (High/Medium/Low) | Current Engagement Level | Potential Management Strategies |
| --- | --- | --- | --- |
| David Chan | High / High | Actively Engaged | Maintain daily stand-ups; use clear reporting; ensure continuous risk and scope management. |
| Nina Patel | High / High | Highly Engaged | Provide regular high-level updates; involve in milestone reviews; align with HR strategic goals. |
| Mark Rivera | High / High | Highly Engaged | Present clear financials; involve in budget reviews; emphasize ROI; formal communication preferred. |
| Liam Kapoor | High / High | Overly Involved | Channel technical enthusiasm; set clear priorities; limit scope influence; regular technical check-ins. |
| Chloe Nguyen | Medium / High | Actively Engaged | Support requirements process; ensure clear documentation; facilitate stakeholder workshops. |
| Omar | Medium / High | Highly Engaged | Formalize feedback process; involve in UAT; prevent scope creep via PM coordination. |
| Isla Romano | Medium / Medium | Moderately Engaged | Provide structured financial data; align with Omar carefully; formal updates. |
| Ethan Morales | Medium / Medium | Engaged | Assign clear tasks; peer reviews; align with Liam on technical delivery. |
| Patrick Lamar | Medium / Medium | Engaged | Monitor availability; plan for knowledge transfer; engage during integration phases. |
| Noah Zhang | Low / Medium | Limited Engagement | Engage as needed; assign specific infrastructure tasks; monitor performance. |
| BrightPath Consultants | Medium / Medium | Contractually Engaged | Manage via SOW; regular progress reviews; align training with rollout schedule. |
| End Users | Low / High | Not Yet Engaged | Conduct surveys & focus groups; involve pilot groups; provide clear training & communication. |

A. Stakeholder Strategy: Liam Kapoor (Programmer / AI Specialist)

Challenges Identified

- Over-involvement in technical details

- Pushes for perfection → delays

- Often attempts to shift priorities (scope drift)

- Tendency to rewrite code unnecessarily

Management Strategy

1. Define “Done” with Non-Negotiable Acceptance Criteria

- Create a formal “definition of done” for AI and programming tasks.

- Include accuracy thresholds, performance benchmarks, UI guidelines.

- Prevents endless perfection cycles.

2. Implement a “Two-Review Rule”

- Allow only two rounds of revision unless a defect is found.

- This protects timeline while still respecting his expertise.

3. Assign Liam as AI Quality Lead, not Scope Owner

- He validates AI logic but cannot change requirements without PM approval.

- Redirects his passion to quality—not altering priorities.

4. Weekly 15-minute “Tech Alignment Check-ins”

- Quick sync to ensure he channels innovation into structured areas.

- Reduces unsanctioned tinkering.

5. Use Data to Manage Perfectionism

- Show the schedule impact of extended rewrites.

- Frame decisions around schedule and budget constraints, not opinion.

B. Stakeholder Strategy: Nina Patel (VP of HR, Co-Sponsor)

Challenges Identified7

- Focuses heavily on long-term cultural impact

- Slows decision-making

- Difficulty aligning with tactical milestones

Management Strategy

1. Use Dual-Track Decision Framework
 Separate discussions into:

- Track A: Immediate deliverables & deadlines

- Track B: Long-term HR culture & adoption plans

This prevents philosophical debates during tactical decisions.

2. Provide Visual Roadmaps

- Show how short-term tasks feed into long-term HR transformations.

- Helps her see alignment without delaying current milestones.

3. Pre-Meeting Previews

- Send condensed briefs 48 hours in advance.

- Ensures she processes “big-picture concerns” before meetings.

4. HR Benefits Dashboard

- Translate technical tasks into HR outcome metrics (engagement, health improvement).

- Helps her stay grounded in deliverables.

C. Stakeholder Strategy: Mark Rivera (VP of Finance, Co-Sponsor)

Challenges Identified

- Extremely risk-averse

- Micromanages budget approvals

- Causes procurement and hiring delays

- Prefers formal communication; dislikes ambiguity

Management Strategy

1. Provide “Triple-Clarity Packs” for Every Decision
 Every request includes:

- Financial impact (quantified)

- Risk assessment

- Decision required + suggested option
 This drastically shortens his approval time.

2. Use Strict Change Control on Costs

- Highlight that unapproved delays increase costs.

- Demonstrate that structured approvals reduce risk.

3. Weekly Budget Health Dashboards

- CPI, SPI, Forecast vs Baseline

- Show spending discipline clearly and proactively.

4. Use Formal Written Communications

- Executive summaries

- Financial justification sheets

- Attach all backup details

D. Stakeholder Strategy: Omar Alvi (HR SME)

Challenges Identified

- Bypasses protocols

- Makes last-minute changes

- Influences development team directly without PM coordination

- Creates misalignment between HR and IT

- Strong opinions can derail structured meetings

Management Strategy

1. Establish a “Single Source of Truth Requirement Log”

- All requests must go through the PM or Business Analyst.

- Prevents direct changes to dev team.

2. Implement a Formal Change Request (CR) Process

- Any new feature or change → CR form

- Requires impact analysis + PM approval

- Eliminates impulsive requirement injections.

3. Assign Omar a Structured SME Role

- “Voice of Employee Experience”

- His input is valuable but confined to scheduled checkpoints.

4. Use Time-Boxed Discussion Windows

- Allow 10–15 minutes in workshops for Omar to present HR concerns.

- Protects against derailment.

5. Mediate HR–Finance Conflicts

- Schedule joint requirement sessions with Isla to avoid tension.

- PM ensures both perspectives are heard and documented.